## Project Metrics
Data in blue italics is completely fictitious and is there for guidance.
Project Metrics | [5 empty] | Reference: This template is closely modeled after the “PSP Project Plan Summary” form provided in Introduction to the Personal Software Process by Watts S. Humphrey (1997).
Metric | Plan | Actual | Cumulative |  |  | Sanity Checks
Minutes / LOC | 8 | 9 | 6.6364
LOC / Hour | 7.5 | 6.6667 | 9.0411
Defects / KLOC | 80 | 51.3636 | 59.0909
Pre-Compilation Yield % | 62.5 | 73.4513 | 62.3077
Appraisal / Failure Ratio | 0.3 | 0.35366 | 0.29508 |  |  | 0.35366
Program Size (LOC) | Plan | Actual | Cumulative
Total New & Changed | 1500 | 2200 | 55000
Maximum Size | 1650
Minimum Size | 1350
Time in Phase (minutes) | Plan | Actual | Cumulative | Cumulative %
Requirements | 2500 | 3000 | 75000 | 20.5479
Design - creation | 1500 | 3000 | 42500 | 11.6438
Design - review / rework | 500 | 900 | 17500 | 4.7945
Implementation - coding | 1500 | 2700 | 50000 | 13.6986
Implementation - code review / rework | 1000 | 2000 | 27500 | 7.5342
Implementation - code build / rework | 1000 | 1500 | 27500 | 7.5342
Test | 4000 | 6700 | 125000 | 34.2466
Total | 12000 | 19800 | 365000 | 100 |  | 12000
Maximum Time | 13200
Minimum Time | 10800
Defects Injected | Plan | Actual | Cumulative | Cumulative % | Defects / Hour
Design - creation | 50 | 40 | 1375 | 42.3077 | 1.375
Implementation - coding | 70 | 73 | 1875 | 57.6923 | 1.6667
Test
Total | 120 | 113 | 3250 | 100
Defects Removed | Plan | Actual | Cumulative | Cumulative % | Defects / Hour
Design - review / rework | 50 | 50 | 1375 | 42.3077 | 1.375
Implementation - code review / rework | 25 | 33 | 650 | 20 | 0.37143
Implementation - code build / rework | 25 | 20 | 650 | 20 | 0.37143
Test | 20 | 10 | 575 | 17.6923 | 0.276
Total | 120 | 113 | 3250 | 100
Note on A4: The values captured in this top-most section show the real value-add for this type of data tracking. These values provide very useful indicators of performance improvements or performance regressions as the arrow of time moves forward for your organization.
Note on A8: 100*(pre-compilation defects removed) / (pre-compilation defects injected)
Note on A9: = appraisal_cost_of_quality / failure_cost_of_quality appraisal_cost_of_quality = (100 * total_review_time) / total_development_time failure_cost_of_quality = (100 * (implementation_build_time + test_time)) / total_development_time
Note on A14: Taking these measurements precisely and accurately will require discipline. Software engineers must meticulously record how they are spending their time in time logs.
Note on A25: Detailed defect logs must be maintained throughout the software development process life cycle in order to capture the raw data required by this worksheet.
Note on A26: These are the defects that are found either during the design review or during coding / code review / code build that are attributed to problems with the design.
Note on D4: Running total (or calculations based on running totals) across all projects that have been completed including all work to-date on the current project